## Slide 1: Inner Triplets upgrade – 2013 Very first Schedule
17 july 2008

## Slide 2: Draft sum of durations
Warm-up 4wks
From RP OK to enter
  HLS removal & IT reference 6 days
  (hidden time if OK from RP during warm-up)
From RP OK to disconnect
  IT disconnections 4wks
  QRL modifications ????
  Transport - Jacks (removal & new) 4wks
  Alignement 1wk
  Interconnections 15wks
  Leak test 2 wks
  30 wks

## Slide 3: Draft and summarized schedule
Warm-up
SU
Disconn.
Transport
SU
Disconn.
LT
SU
Disconn.
Transport
SU
Disconn.
LT
Disconn.
Transport
SU
Disconn.
LT
Disconn.
Transport
SU
Disconn.
LT
SU
SU
1 machine for disconnection and 1 set of transport equipment
SU
Disconn.
Transport
SU
Disconn.
LT
SU
Disconn.
Transport
SU
Disconn.
LT
Disconn.
Transport
SU
Disconn.
LT
Disconn.
Transport
SU
Disconn.
LT
SU
SU
2 machines for disconnection and 2 sets of transport equipment
Not including QRL modifications

## Slide 4: List of activities
1. Main ring
  1.1 Removal
  1.2 Installation
  1.3 Tests
2. UJ
  2.1 Removal
  2.2 Installation
  2.3 Tests

## Slide 5: List of activities – 1. Main ring
Removal
  Services
    HLS & WLS removal 3d H. Mainaud-Durand
    IT survey references 3d H. Mainaud-Durand
    BLM, BPM, PMIL removal 1d
    WCC removal 2w J.-C. Guillaume
    Cryo instrumentation removal ? ?
    Electrical general services modification ? ? J. Pierlot
  Machine removal
    TAS displacement ? ATLAS & CMS
    IT disconnections 4w J.-P. Tock
    QRL modifications ? ?
    D1 disconnections ? ? ?
    Transport and jacks ~2w S. Bartolome
    Vacuum chambers & supports removal ? V. Baglin

## Slide 6: List of activities – 1. Main ring
Installation
  Services
    Transport and Jacks 2w S. Bartolome
    Alignment 1w H. Mainaud-Durand
    HLS & WLS installation 2w H. Mainaud-Durand
    BLM, BPM, PMIL installation ?
  Machine
    Interconnections 15w J.-P. Tock
    Leak tests 2w P. Cruikshank
    Cryo intrumentation ? ?
    TAS replacement and VAC chamber ? ?
    VAC between IT and TAN ? V. Baglin

## Slide 7: List of activities – 1. Main ring
Tests
  Cool-down
  ELQA
  QPS
  Powering tests

## Slide 8: List of activities – 1. UJ
Removal
    Sheilding 3d S. Pelletier
    Access system (per system) 1d E. Sanchez
    (from point 1 to point 2, and from point 5 to point 2)
    Wire fencing
    Racks reorganization : what is to be done ?
Installation
    DFBX installation 1d C. Bertone
    DFBX connections with IT
    WCC ? Or other type of cables
    DQR and DQS installation
Tests
    Short circuit tests ?